## checklist
Category | Task | Task Owner | Target Completion Date | Completion Date | See also doc #
1. Project Development and Space Selection
1.1 | Develop timeline and project schedule | RE Comm | 2016-09-15 | 2016-09-15
1.2 | Employee census and occupancy review | RE Comm | 2016-07-01 | 2016-07-01
1.3 | Site survey and facility review of current and proposed locations | RE Comm | 2016-07-01 | 2016-07-01
1.4 | Desired square footage needed at new location | RE Comm | 2016-07-01 | 2016-07-01
1.5 | Floor plan for new space that identifies work stations, equipment centers, offices, conference room needs, fixtures, and other support spaces (include seating assignments for all) | RE Comm, DMD | 2016-09-23
1.6 | Architect for new construction, upgrades and/or buildouts | RE Comm | 2015-05-01 | 2015-05-15
1.7 | Office relocation budget | RE Comm, JJB
1.8 | Bid and award moving contract | RE Comm, JJB
1.9 | Other design items |  |  |  | 2704002
2. Technology
2.1 | IT infrastructure assessment of current and proposed locations | JDG
2.2 | Inventory of all technology assets | JDG
2.3 | Evaluation of current cabling and network via industry best practices | JDG
2.4 | Evaluation of technology upgrades for potential project consolidation | JDG
2.5 | Inventory of critical business and support applications | JDG
2.6 | Evaluation of network downtime options versus redundant hardware and applications during cut over | JDG
2.7 | Desktop relocation support strategy and resources | JDG
2.8 | Identify any changes necessary to be made in Aderant for new address | TAB
2.9 | Evaluate other equipment (take v. replace) - fax machines, postage machine, other? | JJB
2.101 | Evaluation of power, AC, ventilation, network and equipment positioning requirements | JDG, TAB, JJB
3. Selection of furnishings and equipment
3.1 | Furniture selection criteria and specifications | RE Comm, DMD
3.2 | Comprehensive furniture inventory | TAB, JJB
3.3 | Evaluation of furniture options: Reuse existing furniture Repurpose existing furniture Purchase new furniture Purchase refurbished options Sell/decommission old furniture | TAB, JJB, DMD
3.4 | Order needed office furniture | TAB, JJB
3.5 | Evaluate artwork - taking v. discarding | RE Comm, DMD
3.6 | Choose elevator lobby and/or reception signage | RE Comm, DMD
3.7 | Purchase signage | TAB, JJB
3.8 | File all warranty info for new furniture & equipment | TAB
3.9 | Identify new equipment wanted in new office | TAB, ? |  |  | 2704002
4. Telecom
4.1 | Evaluation of phone system: order new or relocate existing | JDG
4.2 | Phone numbers: order new or transfer existing through carrier | JDG
4.3 | Data services: order new or transfer existing (POTS, T-1, ISDN, DSL) | JDG
4.4
5. Paper and Supplies
5.1 | Manage supplies as move date approaches | JJB
5.2 | Order all printed materials with new address (stationery, business cards, envelopes, bill paper, ___________ ) | JJB
5.3 | Notify banks of new address and order new checks for all firm accounts (remind attorneys who have individual escrow accounts to do the same) | TAB
5.4 | Order name plates for all | JJB
5.5 | Order move t-shirts | KTK
6. Communications
6.1 | Internal communications plan for employees | ALL
6.1.1 | Schedule regular meetings, update personnel on new office progress
6.1.2 | Arrange for staff to tour new premises a few weeks prior to move |  | 2017-05-01
6.1.3 | Add New Office section to FYI
6.1.4 | Organize fun stuff - ideas: | ?
Guess how many truckloads the firm will ship to its new location
Guess the exact minute TAB opr WWC will leave a message letting everyone know they can enter the building
| Design and purchase MOVE t-shirt (have design contest?) | DMD?
Have firm leaders come up with contest gifts
Conduct poll re: everyone's favorite and least favorite piece of art
6.1.5 | Prior to move - All Personnel MOVE Meeting - give out 'move' t-shirts, review: | TAB | 2017-06-01 |  | 2704002
| Packing procedures (see doc 2137698) | TAB
| New building rules | TAB
| Parking procedures | TAB
| Network outage and contingency plan | JDG
| Phone list - update for personnel, conf rooms, other spaces | KTK
6.1.6 | Put together branding welcome pack for staff (internal map, printer locations, coffee mug filled with candy, other branded gift) | KTK, DMD
6.2 | Create communications plan for clients, courts, opposing counsel, other lawyers, referral sources, government agencies, bar associations, announcements, website, social media sites, other?
6.2.1 | Building signage | RE Comm, DMD
6.2.2 | Update website and print and e-collateral materials to reflect new information | DMD
6.2.3 | Revise advertising (including Yellow Pages and other directories) | DMD
6.2.4 | Notify post office of change of address | JJB
6.2.5 | Message scripts for communicating with external constituents | DMD
6.2.6 | Announcements mailed | DMD
6.2.7 | Vendors – notify re: change of address - supply or update your mailing list w/DMD if you want vendors to get an e-announcement related to move and new address | All
6.2.8 | Notify others as indicated above in 6.2 | All
6.2.9 | Email campaigns: (1) pre-move: announce upcoming move and (2)on move date: announce new address | DMD
6.2.10 | Press release | DMD
6.3 | Plan party - employees, clients, etc. - once in new space | DMD
7. Document Management (hard copy files)
7.1 | Plan for on-site storage needs | RE Comm
7.2 | Continue file cleanup efforts | TAB, JJB |  |  | 2704002
7.3
8. Move Preparation
8.1 | Identify building restrictions for move hours | JJB
8.2 | Schedule parking and unloading at old and new sites | JJB
8.3 | Obtain any special moving and/or parking permits | JJB
8.4 | Reserve elevators & loading docks for moving day | JJB
8.5 | IT staff to manage disconnect and reconnect of servers and data centers | JDG
8.6 | Arrange to have sensitive items packed and moved | JDG
8.6.1 | Computers | JDG
8.6.2 | Telephone equipment | JDG
8.6.3 | Networking equipment and servers | JDG
8.6.4 | Copiers | JDG
8.7 | Determine employee packing requirements | JJB
8.8 | Determine common area packing requirements | JJB
8.9 | Order packing supplies (ask mover about crate rental vs. boxes) | JJB
8.101 | Communicate packing/labeling guidelines – professional movers will provide custom packing instructions and labels | TAB, JJB
8.10.1 | Color-code furniture to a color-coded floor plan?
8.11 | Packing schedule: determine what can be packed in advance vs. last minute so your business can continue to operate as efficiently as possible with the least amount of interruption | TAB, JJB
8.12 | Ask employees to take valuables or fragile items home (includes partners with personal furniture that won't be moved) | TAB
8.13 | Ensure boxes or containers are properly packed and labeled with office location or name, importance, and contents | JJB
8.14 | Order parking cards and ensure they come in | KTK
8.15 | Order building access cards and ensure they come in | JJB
8.16 | Check insurance coverage for move | TAB
8.17 | Distribute building access cards to everyone | JJB
8.18 | Collect and return old building access cards | JJB
8.19 | Distribute parking cards | KTK
8.201 | Collect and return old parking cards | KTK
8.21
9. Vendor arrangements
9.1 | Furniture installation/reconfiguration | TAB, JJB
9.2 | Cabling | JDG
9.3 | Telephone/data (POTS, T-1, ISDN, DSL) | JDG
9.4 | Network (upgrade, back up, prepare for move) | JDG
9.5 | Security system | TAB, JJB
9.6 | Secure document destruction and removal | TAB, JJB
9.7 | Janitorial | JJB
9.8 | Plant watering | JJB
9.9 | Vending | JJB
9.1 | Supplies | JJB
9.11 | Courier | JJB
9.12
9.13
10. Moving Day
11.1 | Have A/C on - both locations | JJB
11.2
11.3
11.4
11.5
11. After move
11.1 | Distribute branded 'welcome pack' for employees | KTK
11.2 | Artwork to be hung in public spaces (and in offices?) - make special arrangements | JJB
11.3 | First aid kits mounted | JJB
11.4 | Employee Move Orientation Meeting (include security, fire & safety procedures) | KTK
11.5 | Hang bulletin boards – HR stuff | KTK, JJB
11.6 | Follow up on all remaining punch list items | TAB
11.7 | Ensure lobby directory is updated | TAB
11.8
11.9